| Klinck Data Centre: Data and Workload Migration Project Charter |
| --- |
| UBC IT |  |  |

Revision History

| Version # | Author | Date | Reviewed By | Approved By | Description of Change |
| --- | --- | --- | --- | --- | --- |
| 1.0 | Laszlo Hollander | 21 September 2013 |  |  |  |
| 1.1 | Mario Angers | 25 September 2013 |  |  | Edit and additions |
| 1.2 | Laszlo Hollander | 26 September 2013 |  |  | Edit and additions |
| 1.3 | Laszlo Hollander | 28 September 2013 |  |  | Edit and additions |

Document References

| Short Name | Document Description | Version | File Name |
| --- | --- | --- | --- |

Table of Contents

Project Background	3

Project Objectives & Success Criteria	3

Project Scope	3

Milestones & Deliverables	4

Resources	4

Project Approach	4

Assumptions	5

Dependencies	5

Constraints	5

Project Risks	5

Project Organization	6

Project Authorization	7

Appendices	7

Appendix A:  Detailed Project Schedule	7

Appendix B:  Communication Plan	7

# Project Background

The Klinck Data Centre (KDC) will be decommissioned and shut down in 2015. Vendor support for the hardware of KDC’s virtual infrastructure is expiring at the end of 2013. The renewal of the support for $600.000 per year is cost prohibitive. The same amount would allow the purchase of new hardware equivalent to what is in KDC today. Furthermore, the new hardware could be used for the next 5 years.

UBC IT will be moving all production virtual servers and storage by the end of 2013 and all other virtual servers and storage by the end of 2015 from KDC to the new University Data Centre (UDC) in the Pharmaceutical Sciences Building. In UDC the storage is consolidated and re-organized from several storage islands to one physical and logical unit. This gives our infrastructure the scalability, performance, fault tolerance and manageability required to meet current and future needs. The storage cluster will also eliminate the need to disrupt services when hardware upgrades are required.

In Phase 1 of the project, all production data and workload will be evacuated from KDC before the service maintenance runs out. In Phase 2 of the project, all development and test data and workload will be moved.

# Project Objectives & Success Criteria

The objective of the project is to successfully evacuate all virtual machines (VMs) and data stores, then shutting down and decommissioning KDC.

The success is defined as:

- Production VMs and data stores moved from KDC

- Development and test VMs and data stores moved from KDC

- Functionality of services offered by VMs and data stores moved to target data centre are retained as they were before the move

- Equal or better performance of VMs and data stores provided in target data centre

- Outages of services caused by the migration are kept to a minimum

# Project Scope

- Phase 1

  - Complete assessment of production workload and data

  - Develop communication plan

  - Develop migration plan of production data and workloads

  - Migrate production data and workloads from KDC by 31st December 2013

- Phase 2

  - Complete assessment of development and test workload and data

  - Develop communication plan

  - Develop migration plan of development and test data and workloads

  - Migrate development and test data and workloads from KDC by the end of 2015

# Milestones & Deliverables

| Project Milestones – Phase 1 | Target Date |
| --- | --- |
| Complete Assessment of Production Workload and Data | 6 September 2013 |
| Develop Communication Plan | 29 May 2013 |
| Client Communication | 31 December 2013 |
| Develop Migration Strategy | 27 September 2013 |
| Develop Risk Mitigation Strategy | 27 September 2013 |
| Execute Migration Plan | 31 December 2013 |

| Project Milestones – Phase 2 | Target Date |
| --- | --- |
| Complete Assessment of Development and Test Workload and Data | 6 June 2014 |
| Develop Communication Plan | 28 February 2014 |
| Client Communication | 31 December 2014 |
| Develop Migration Strategy | 27 June 2014 |
| Develop Risk Mitigation Strategy | 27 June 2014 |
| Execute Migration Plan | 31 December 2014 |

# Resources

| Resource | Description & Source |
| --- | --- |
| UBC IT Systems | Perform migration |
| UBC IT NMC | Change network configuration |
| UBC IT Database group | Assist with database moves |
| UBC IT Service Centre | Assist with monitoring of infrastructure |
| UBC IT Client Service Managers | Set expectations for service owners |
| UBC IT Communications | Communicate with service owners and UBC community |
| Service, Application, and Systems owner | Communicate to own clients and approve move Verify list of virtual servers and data stores to be moved Provide appropriate outage windows Provide virtual server shutdown and startup sequence Validate functionality of moved environment |

# Project Approach

The approach that will be taken to complete the project and produce the deliverables are:

- Complete Assessment of Existing Workload and Data

  - Organize workload and data based on grid, service, clients, and cluster

  - Prioritize transition by client and/or service

- Develop Communication Plan

  - Create and schedule the publishing of web and email based communication

- Client Communication

  - Schedule information sessions to provide overview of migration plan and gather migration information

- Develop Migration Strategy

  - Test migration methodologies and generate operational checklist

- Develop Risk Mitigation Strategy

  - Ensure resources are available

- Execute Migration Plan

  - Based on defined VM and storage structure

# Assumptions

UBC IT Senior Management evaluated and agreed with the recommended approach and scope of this project.

# Dependencies

| Dependency | Impact |
| --- | --- |

# Constraints

| Dimension | Constraint |
| --- | --- |
| Schedule – Phase 1 | Migration of the production environment needs to be completed before the 31st of December 2013 or before manufacturer’s support runs out on Klinck data centre infrastructure |

# Project Risks

| Risk | Probability | Impact | Response Strategy |
| --- | --- | --- | --- |
| Service owner does not agree to move | 4 – Likely | 4 – Major | Mitigation: No move or move to LFSC |
| Service owner does not commit to migration date | 4 – Likely | 4 – Major | Mitigation: No move or move to LFSC |
| Service owner cancels last minute migration at the agreed upon date/time | 4 – Likely | 3 – Significant | Mitigation: reschedule move |
| UBC IT Systems resources are not available at the time of migration | 1 – Very Unlikely | 3 – Significant | Avoidance: schedule backup staff |
| Non-UBC IT Systems resources (NMC, DBA…) are not available at the time of migration | 1 – Very Unlikely | 3 – Significant | Mitigation: reschedule move |
| Service owners are not available to verify migrated VMs functionality | 1 – Very Unlikely | 2 – Minor | Mitigation: verification done at a later time |
| Network service interruption | 1 – Very Unlikely | 2 – Minor | Mitigation: reschedule move |
| KDC service interruption | 1 – Very Unlikely | 2 – Minor | Mitigation: reschedule move |
| UDC service Interruption | 1 – Very Unlikely | 2 – Minor | Mitigation: reschedule move |
| Power outage | 1 – Very Unlikely | 2 – Minor | Mitigation: reschedule move |
| Data migration causes service instability or service degradation | 2 – Unlikely | 3 – Significant | Mitigation: reschedule move |

# Project Organization

The following table identifies the roles and responsibilities of the project team members:

| Role | Responsibilities |
| --- | --- |
| Executive Sponsor Mario Angers | Acts as the project champion and communicates project mandate to the organization Authorizes resources for the project Ultimate decision-maker for the project Measures and evaluates success of the project; accountable for the project benefits |
| Project Manager Laszlo Hollander | Accountable for the completion of the project deliverables Manages the project budget and team resources Manages issues and risks Manages changes through CAB process Point person for communications around the project |
| UBC IT Systems Team | Completes and validates migration tasks Ensures that technical risks are identified and managed |

# Project Authorization

The signatures below represent an authorization to proceed with the project as defined in this Charter document including Appendices.

| Role | Name & Title | Date |
| --- | --- | --- |
| Executive Sponsor | Mario Angers, Senior Manager, UBC IT Systems |  |

# Appendices

## Appendix A:  Detailed Project Schedule

## Appendix B:  Communication Plan